## Hoja1
Arquitectura de Sistemas (2019-2020)
|  | Sept: 04-06 | Sept: 09-13 | Sept: 16-20 | Sept: 23-27 | Sept: 30 - Oct: 04 | Oct: 07-10 | Oct: 14-18 | Oct: 21-25 | Oct: 28-31 | Nov: 04-08 | Nov: 11-15 | Nov: 18-22 | Nov: 25-29 | Dic: 02-05 | Dic: 10-15 | TOTAL horas
Planificado | Tomek | [10 empty] | ACT 2(3h) | ACT 4(1h), 6(2h) | ACT 8(0,5h) | ACT 9(1h) | ACT 10(3h), 13(2h), 14(1h), 17(0,5h)
Realizado | Tomek
Planificado | Michal | [10 empty] | ACT 3(3h) | ACT 4(1h), 5(2h) | ACT 8(0,5h) | ACT 9(1h) | ACT 10(3h), 11(0,5h), 12(0,5h), 17(1h)
Realizado | Michal | [10 empty] | ACT 3(6h) | ACT 4(0,5h), 5(1h) | ACT 8(0,5h) | ACT 9(1h) | ACT 10(5h), 11(1h), 12(1h), 17(1h)
Planificado | Will | [10 empty] | ACT 1(2h) | ACT 4(1h), 7(2h) | ACT 8(0,5h) | ACT 9(1h) | ACT 10(3h), 15(1h), 16(0,5h), 17(0,5h)
Realizado | Will
Tabla donde se describen las actividades de todos los integrantes del equipo
ACT 1 |  | Create the menu
ACT 2 |  | Create structure to hold acces point information
ACT 3 |  | Implement reading functionality
ACT 4 |  | Update our files using the templates provided for the project
ACT 5 |  | Finish up the wificollector_collect functionality now that the basic data structure has been built data structure has been built
ACT 6 |  | Work on improving the last task
ACT 7 |  | Create a function to display a single wifi structure
ACT 8 |  | Upload partial version
ACT 9 |  | Go to appointment with professor
ACT 10 |  | Finish up the things from left-to-do list
ACT 11 |  | Go through all Minutes and correct them if necessary
ACT 12 |  | Write Minutes from last two meetings
ACT 13 |  | Solve Ctr-D problem on Debian
ACT 14 |  | Correct debug mode where necessary
ACT 15 |  | Add templates where missing
ACT 16 |  | Add comments where needed
ACT 17 |  | Fill in the activity sheet